## RCA
ROOT CAUSE ANALYSIS (RCA) REPORT
ORGANIZATION
AGENCY | xyz company
REFRENCE NUMBER
PROGRAM/FACILITY
REGION | APAC
TRACKING ID | 122345
PRIMARY CONTACT DETAILS | NAME: | Andrew
PHONE:
EMAIL:
DATE OF EVENT: |  | DATE RCA COMPLETED:
EVENT DETAILS
EVENT DESCRIPTION |  | LIST RCA TEAM MEMBER
of our Deliverable 45 review process, we notified xyz company of an open item (SLA-19 security patches have not been applied to offline servers for the past two months). Xyz company has responded stating that they are still investigating whether the pacthes are still missing or if it is a false positive. CS team ticket 202172 has been opened , there is no ETA as of now.
TEAM LEADER/SUPERVISOR:
BACK GROUND SUMMARY
Answer these questions with a brief summary - attach supporting documents if available
what were the expected sequence of events that were to take place? Attach fow chart if avaiable. |  | As soon as team was made aware, we started looking into application logs. When we logged into servers, we observed server response time was slow. Within couple minutes we got an alert that CPU was 100%, we restarted servers to bring application back into busines.
Was there any deviation from the expected sequence, was it likely to have contributed to advance event?
If deviation ocured from the expected sequence describe in policy, procedure, written guidelines, or included in staff training?
Was the expected sequence described in policy, procedure, written guidelines, or included in staff training? |  | Yes, team is aware of the steps when this type of situation happens.
Does the expected sequence meet regulatory requirements and/or practice standards? |  | Yes, our documenation meets requirements and standard practices.
Was there a human action or inaction that contributed to the adverse event? |  | There was no human action or inaction that contributed to the event.
Was there a defect, malfunction, misuse of, or absence of equipment that contributed to this event? |  | We have a unknown at this point regarding CPU hitting 100%. We have not observed this behaviour on the application servers since it happened.
Did the procedure/activity involved in the event being carried out take place in the usual location?
Was the procedure/activity carried out by regular staff familiar with the consumer and activity? |  | Yes, Xyz Comapny team took necessary action as needed to bring application back.
Did the involved staff have the correct credentials and skilled to carry out the tasks expected of them? |  | Yes, xyz company team members has credentials and necessary access.
Was the staff trained to carry out their expected responsibilities? |  | SRE team are trained to handle such responsibilities
Were the staffing levels considered adequate at the time of the incident?
Were there any additional staffing factors identified as responsible for or contributing to the adverse event?
Was there any inaccurate or ambiguous information that contributed to or caused the adverse event?
Was there any lack of communication or incomplete communication that contributed to or caused the adverse event?
Were there any environmental factors that contributed to or caused the adverse event?
Were there any organizational or leadership factors contribute to or cause the adverse event?
Was there any assessment or planning factors that contributed to or caused the adverse event?
Were there any other factors that are considered relevant to the adverse event?
Were there any other factors that are considered relevant to the adverse event?
Rank in order the factors considered responsible for the adverse event, beginning with the proximate cause, followed by the most important to less important contributory factors. Attach Contributory Factors Diagram, if available.
Was there a root cause identified? |  | As of now, SRE team have not found the root cause of the server behaviour. But SRE team is watching the notifications regularly if CPU is hitting 100%. SRE team has created a ticket to investigate further and will colaborate with Dev team - Ticket 12334
RISK REDUCTION ACTIONS TAKEN
List the actions that have already been taken to reduce the risk of a failure occurrence. Note the date of implementation.
DATE | EXPLAIN ACTION TAKEN
2024-01-01 | We are working with development team to see why CPU was hitting 100% on the application servers. Continue to minitor alerts in case application is down and take appropriate action immediately.
PREVENTION STRATEGIES
List the recommended actions planned to preent a failure occurrence of the adverse event. Begin with a rank of 1 (hihest). Provide an estimated cost (if known) and any additional considerations/recommendations for implmenting the strategy.
STRATEGY | ESTIMATED COST | SPECIAL CONSIDERATIONS
Continue to monitor alerts in dtect potential outages and take action accordingly.
INCIDENTAL FINDINGS
List and explain any incidental findings that should be carefully reviewed for corrective action.
We are working with development team to see why CPU was hitting 100% on the application server.
APPROVAL
After review of this summary report, all team membes should notify the team leader of either their approval or recommendations for revision. Following all revisions the report should be signed by the team leader prior to submission.
SIGNATURE OF TEAM MEMBERS: |  | DATE SIGNED:
Varun |  | 2024-01-01
All information included in this report is considered confidential. It is intended only to promote safety and reduce risk.
Forward completed report to all Root Cause Analysis team members in additiona to the following individuals.
FULL NAME | TITLE/ORGANIZAION | EMAIL ADDRESS
VARUN | GRC | VKUMA5@OUTLOOK.COM
YES
NO
YES
NO
UNKNOWN
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN
YES
NO
YES
UNKNOWN

## Summary
Incident Overview
During a routine operational period, the application experienced a performance degradation event that resulted in service disruption. The Site Reliability Engineering (SRE) team was alerted after observing slow server response times upon logging in, which was shortly followed by a critical alert indicating CPU utilization had reached 100%. As an immediate remediation step, the servers were restarted to restore normal business operations.
Current Investigation Status
The root cause of the abnormal CPU behavior has not yet been identified. The SRE team is actively monitoring CPU thresholds and has raised Ticket 12334 under Deliverable 45 to formally investigate the issue in collaboration with the Development team.
Parallel Security Finding
Separately, during the Deliverable 45 review process, Xyz Comapny was notified of an open security compliance item (SLA-19), which flagged that security patches had not been applied to offline servers for the preceding two months. Xyz Comapny is currently determining whether the patches are genuinely missing or whether the alert is a false positive. CS Team Ticket 202172 has been opened to track this item, with no estimated time of resolution at this stage.